## Trang tính1
Total Project Tracking - GitHub Linked
# | Screen/Function | Feature | Actor | Screen/Function Description | In Charge | Status | Actual | Updated | Update Details | GitHub URL
1 | Login | Authentication | Customer, Staff, Manager, Admin | User logs into the system | Tuấn Anh | Done | Iteration 1 | 2026-05-26 | Completed authentication baseline; linked to auth controller/service. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/controllers/auth.controller.ts
2 | Register | Authentication | Customer | Customer creates a new account | Tuấn Anh | Done | Iteration 1 | 2026-05-26 | Completed customer registration API and form flow. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/controllers/auth.controller.ts
3 | Setup Health Profile | Authentication | Customer | Customer sets up health profile and allergy information | Tuấn Anh | Done | Iteration 1 | 2026-06-23 | Completed health profile and allergy conflict UI/API refinement. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/206
4 | Forgot Password | Authentication | Customer, Staff, Manager, Admin | User requests password reset | Tuấn Anh | Done | Iteration 1 | 2026-05-26 | Completed OTP email verification and reset flow. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/controllers/auth.controller.ts
5 | Change Password | Authentication | Customer, Staff, Manager, Admin | User changes account password | Tuấn Anh | Done | Iteration 1 | 2026-05-26 | Completed password update endpoint and validation. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/services/auth.service.ts
6 | Logout | Authentication | Customer, Staff, Manager, Admin | User logs out of the system | Tuấn Anh | Done | Iteration 1 | 2026-05-24 | Completed token revoke and cookie clear flow. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/utils/cookies.ts
7 | View Profile | Authentication | Customer, Staff, Manager, Admin | View personal profile information | Tuấn Anh | Done | Iteration 1 | 2026-05-27 | Completed profile UI and account detail retrieval. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/controllers/user.controller.ts
8 | Edit Profile | Authentication | Customer, Staff, Manager, Admin | Update personal profile information | Tuấn Anh | Done | Iteration 1 | 2026-07-22 | Updated delivery/profile address detail with OSM suggestions. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/commit/57e21a9
9 | View Product Details | Product Management | Customer | View detailed product information | Tuấn Anh | Done | Iteration 1 | 2026-06-09 | Completed product detail and null-safe health-risk display. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/149
10 | View Product List | Product Management | Customer | Browse available products | Tuấn Anh | Done | Iteration 1 | 2026-07-02 | Completed product grid, pagination, and product menu total fix. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/224
11 | View Flash Sale | Product Management | Customer | View flash sale products and promotions | Tuấn Anh | Done | Iteration 1 | 2026-06-10 | Completed campaign/flash-sale display support. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/155
12 | Search Products | Product Management | Customer | Search products by keywords | Thiện Hoàng | Done | Iteration 1 | 2026-06-23 | Completed menu search and allergy-aware result refinement. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/206
13 | View Store List | Store Management | Customer | View available stores | Thiện Hoàng | Done | Iteration 1 | 2026-06-18 | Completed store list and current-location store discovery. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/190
14 | View Store Information | Store Management | Customer | View store details and information | Thiện Hoàng | Done | Iteration 1 | 2026-06-06 | Completed store information and store menu browsing. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/137
15 | Filter Products | Product Management | Customer | Filter products by category or criteria | Thiện Hoàng | Done | Iteration 1 | 2026-06-16 | Completed product filtering for customer and admin views. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/185
16 | View Health Warning | Product Management | Customer | View allergy and health warnings for products | Thiện Hoàng | Done | Iteration 3 | 2026-06-23 | Completed health warning flow with allergy-aware smart search. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/193
17 | View Product Recommendations | Product Management | Customer | View personalized product recommendations | Thiện Hoàng | Done | Iteration 3 | 2026-07-10 | Completed personalized recommendation fixes and validation. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/227
18 | AI Recommendation | Product Management | Customer | Receive AI-based food recommendations | Thiện Hoàng | Done | Iteration 3 | 2026-06-10 | Completed AI recommendation with ingredient-aware suggestions. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/146
19 | Chat | Product Management | Customer, Staff | Exchange messages between customer and store staff | Thiện Hoàng | Done | Iteration 3 | 2026-07-16 | Completed chat and chatbot refactor/improvement round. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/232
20 | View Order Details | Order Management | Customer, Staff, Manager | View detailed order information | Thiện Hoàng | Done | Iteration 2 | 2026-06-23 | Completed order invoice, products in history, and status timeline. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/204
21 | View Order History | Order Management | Customer | View previous orders | Thiện Hoàng | Done | Iteration 2 | 2026-06-23 | Completed customer order history with product details. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/204
22 | Cancel Order | Order Management | Customer | Cancel an order before processing | Thiện Hoàng | Done | Iteration 2 | 2026-06-23 | Completed cancel-order logic aligned with confirmOrder flow. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/211
23 | Reject Order | Order Management | Staff, Manager | Reject an order request | Văn Linh | Done | Iteration 2 | 2026-06-23 | Completed store rejection flow aligned with order state machine. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/211
24 | Confirm Order | Order Management | Staff, Manager | Confirm a new order | Văn Linh | Done | Iteration 2 | 2026-06-23 | Completed confirm-order flow and backend status validation. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/211
25 | Update Order Status | Order Management | Staff, Manager | Update order processing status | Văn Linh | Done | Iteration 2 | 2026-06-23 | Completed order status update path with confirmOrder fixes. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/211
26 | View All Orders | Order Management | Staff, Manager | View all orders of the store | Văn Linh | Done | Iteration 2 | 2026-06-04 | Completed store order management table and order list API. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/controllers/order.controller.ts
27 | Apply Voucher | Order Management | Customer | Apply a voucher to an order | Văn Linh | Done | Iteration 2 | 2026-06-22 | Completed voucher tier and freeship validation at checkout. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/201
28 | Place Order | Order Management | Customer | Create and submit a new order | Văn Linh | Done | Iteration 2 | 2026-06-29 | Completed checkout with nearest-store and availability validation. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/215
29 | Payment | Order Management | Customer | Complete payment for an order | Văn Linh | Done | Iteration 2 | 2026-06-06 | Completed PayOS QR payment integration and shipping-fee sync. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/132
30 | Update Shipment Status | Order Management | Manager, Staff | Update shipment status | Văn Linh | Done | Iteration 2 | 2026-06-06 | Completed shipment/status update support for staff workflow. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/services/staff-order.service.ts
31 | Create Store | Store Management | Admin | Create a new store | Văn Linh | Done | Iteration 1 | 2026-05-23 | Completed admin store creation and management baseline. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/80
32 | Update Store | Store Management | Admin, Manager | Update store information | Văn Linh | Done | Iteration 1 | 2026-05-22 | Completed store settings and metadata update support. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/commit/2524e9a
33 | Deactivate Store | Store Management | Admin | Disable store operations | Văn Linh | Done | Iteration 1 | 2026-06-29 | Completed store availability toggle and checkout availability logic. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/216
34 | Activate Store | Store Management | Admin | Enable store operations | Thu Hà | Done | Iteration 1 | 2026-06-29 | Completed store activation path and availability checks. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/216
35 | Toggle Product Availability | Store Management | Staff, Manager | Enable or disable product availability | Thu Hà | Done | Iteration 1 | 2026-07-01 | Completed product availability model refactor to store availability. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/220
36 | View Ingredients | Store Management | Staff, Manager | View ingredient information | Thu Hà | Done | Iteration 1 | 2026-06-06 | Completed ingredients and toppings view. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/136
37 | Edit Ingredients | Store Management | Manager | Update ingredient information | Thu Hà | Done | Iteration 1 | 2026-06-23 | Completed admin menu ingredient editing UI. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/209
38 | Create Product | Store Management | Manager | Add a new product | Thu Hà | Done | Iteration 1 | 2026-05-22 | Completed product CRUD create flow with upload support. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/commit/ad4bdd8
39 | Update Product | Store Management | Manager | Modify product information | Thu Hà | Done | Iteration 1 | 2026-05-22 | Completed product CRUD update flow and filtering operations. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/commit/ad4bdd8
40 | Delete Product | Store Management | Manager | Remove a product from the catalog | Thu Hà | Done | Iteration 1 | 2026-07-01 | Completed product model refactor and soft-delete consistency. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/220
41 | View Product | Store Management | Admin | Approve a product before publication | Thu Hà | Done | Iteration 3 | 2026-06-16 | Completed admin product filter/approval workflow refinement. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/185
42 | Update Voucher | Voucher Management | Manager | Update voucher information | Thu Hà | Done | Iteration 2 | 2026-06-10 | Completed voucher update refactor for admin workspace. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/161
43 | Create Voucher | Voucher Management | Admin | Create a new voucher | Thu Hà | Done | Iteration 2 | 2026-06-10 | Completed create-voucher flow and admin workspace refactor. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/160
44 | Redeem Voucher | Voucher Management | Customer | Redeem a voucher | Khánh Linh | Done | Iteration 2 | 2026-06-21 | Completed valid-voucher validation and redemption flow. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/196
45 | Delete Voucher | Voucher Management | Manager, Admin | Disable an active voucher | Khánh Linh | Done | Iteration 2 | 2026-06-23 | Completed voucher listing/delete refinement in admin workspace. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/208
46 | Write Review | Review Management | Customer | Write a review for an order | Khánh Linh | Done | Iteration 3 | 2026-06-15 | Completed review writing and moderation groundwork. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/175
47 | Upload Review Images | Review Management | Customer | Upload images for a review | Khánh Linh | Done | Iteration 3 | 2026-07-02 | Completed review image moderation and upload handling. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/221
48 | Rate Order | Review Management | Customer | Rate an order experience | Khánh Linh | Done | Iteration 3 | 2026-06-05 | Completed order rating UI and review score capture. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/develop/backend/src/controllers/review.controller.ts
49 | View Comment List | Review Management | Staff, Manager | View customer reviews and comments | Khánh Linh | Done | Iteration 3 | 2026-06-15 | Completed store review moderation/list management. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/175
50 | React To Comment | Review Management | Staff, Manager, Customer | View detailed review information | Khánh Linh | Done | Iteration 3 | 2026-05-22 | Completed review reaction model and API support. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/commit/c3ee8c7
51 | View Campaign | Campaign Management | Manager, Admin | View marketing campaigns | Khánh Linh | Done | Iteration 4 | 2026-06-22 | Completed store-scoped campaign dashboard and campaign view. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/198
52 | Edit Campaign | Campaign Management | Manager | Modify campaign information | Khánh Linh | Done | Iteration 4 | 2026-07-12 | Completed AI campaign edit/profit/timeframe refinements. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/230
53 | Create Campaign | Campaign Management | Manager | Create a new campaign | Khánh Linh | Done | Iteration 4 | 2026-07-14 | Completed AI campaign creation flow and final alignment. | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/231

## Iteration Plan
Project Tracking Iteration Plan
Iteration | Theme | Scope | Date range | GitHub evidence | Metric | Value
Iteration 1 | Foundation & catalog | Auth, profile, browsing, store/product baseline, health/catalog refinements | 2026-05-23 to 2026-07-22 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/206 | Total features | 53
Iteration 2 | Commerce flow | Cart, checkout, order status, payment, shipment, vouchers | 2026-06-04 to 2026-06-29 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/215 | Iteration 1 | 25
Iteration 3 | Engagement & intelligence | Recommendations, AI, chat, reviews, moderation | 2026-06-05 to 2026-07-16 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/232 | Iteration 2 | 15
Iteration 4 | Campaign & final alignment | Campaign CRUD, analytics, AI campaign suggestion, latest polish | 2026-06-22 to 2026-07-14 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/231 | Iteration 3 | 10
[5 empty] | Iteration 4 | 3

## GitHub Sources
GitHub Sources Used For This Update
Type | Reference | Date | GitHub URL | Notes
Repository | SUMMER2026SE/wdp301-rbl-project-group2 | 2026-07-24 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2 | Main GitHub repository used for tracking links.
Current branch | feat/address-detail-osm-suggestions | 2026-07-22 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/tree/feat/address-detail-osm-suggestions | Local branch at update time.
Commit | 57e21a9 feat(checkout): add address suggestions for delivery detail input | 2026-07-22 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/commit/57e21a9 | Latest local commit linked to address detail update.
PR | #232 refactor: chatbot feature | 2026-07-16 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/232 | Chatbot final refactor source.
PR | #231 AI campaign creation | 2026-07-14 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/231 | Campaign creation final alignment.
PR | #227 recommendation fix | 2026-07-10 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/227 | Recommendation correction source.
PR | #224 product menu pagination total | 2026-07-02 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/224 | Product list/menu pagination source.
PR | #221 review image moderation | 2026-07-02 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/221 | Review upload/moderation source.
PR | #215 checkout store availability | 2026-06-29 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/215 | Checkout and place-order validation source.
PR | #211 confirmOrder fixes | 2026-06-23 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/211 | Order transition source.
PR | #206 menu search allergy UI | 2026-06-23 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/206 | Search, allergy, and health warning source.
PR | #201 voucher tier freeship validation | 2026-06-22 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/201 | Voucher checkout validation source.
PR | #190 current location store list | 2026-06-18 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/190 | Store discovery source.
PR | #175 review moderation | 2026-06-15 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/175 | Review management source.
PR | #146 AI recommendation | 2026-06-09 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/146 | AI recommendation source.
PR | #132 payment shipping fee and PayOS | 2026-06-06 | https://github.com/SUMMER2026SE/wdp301-rbl-project-group2/pull/132 | Payment source.